## Project Workplan
Note: Items in yellow are customizable. Calendar week begins on Monday
DGS Procurement Services Sourcing Plan | [6 empty] | Month 1 | [19 empty] | Month 2 | [24 empty] | Month 3 | [19 empty] | Month 4 | [24 empty] | Month 5 | [19 empty] | Month 6 | [19 empty] | Month 7 | [24 empty] | Month 8 | [19 empty] | Month 9 | [19 empty] | Month 10 | [24 empty] | Month 11 | [19 empty] | Month 12
DESCRIPTION | EST DAYS | DAYS | START | FINISH | PRE-REQ | % Complete | 2006-04-03 |  |  |  |  | 2006-04-10 |  |  |  |  | 2006-04-17 |  |  |  |  | 2006-04-24 |  |  |  |  | 2006-05-01 |  |  |  |  | 2006-05-08 |  |  |  |  | 2006-05-15 |  |  |  |  | 2006-05-22 |  |  |  |  | 2006-05-29 |  |  |  |  | 2006-06-05 |  |  |  |  | 2006-06-12 |  |  |  |  | 2006-06-19 |  |  |  |  | 2006-06-26 |  |  |  |  | 2006-07-03 |  |  |  |  | 2006-07-10 |  |  |  |  | 2006-07-17 |  |  |  |  | 2006-07-24 |  |  |  |  | 2006-07-31 |  |  |  |  | 2006-08-07 |  |  |  |  | 2006-08-14 |  |  |  |  | 2006-08-21 |  |  |  |  | 2006-08-28 |  |  |  |  | 2006-09-04 |  |  |  |  | 2006-09-11 |  |  |  |  | 2006-09-18 |  |  |  |  | 2006-09-25 |  |  |  |  | 2006-10-02 |  |  |  |  | 2006-10-09 |  |  |  |  | 2006-10-16 |  |  |  |  | 2006-10-23 |  |  |  |  | 2006-10-30 |  |  |  |  | 2006-11-06 |  |  |  |  | 2006-11-13 |  |  |  |  | 2006-11-20 |  |  |  |  | 2006-11-27 |  |  |  |  | 2006-12-04 |  |  |  |  | 2006-12-11 |  |  |  |  | 2006-12-18 |  |  |  |  | 2006-12-25 |  |  |  |  | 2007-01-01 |  |  |  |  | 2007-01-08 |  |  |  |  | 2007-01-15 |  |  |  |  | 2007-01-22 |  |  |  |  | 2007-01-29 |  |  |  |  | 2007-02-05 |  |  |  |  | 2007-02-12 |  |  |  |  | 2007-02-19 |  |  |  |  | 2007-02-26 |  |  |  |  | 2007-03-05
[7 empty] | 2006-04-03 | 38811 | 38812 | 38813 | 38814 | 38817 | 38818 | 38819 | 38820 | 38821 | 38824 | 38825 | 38826 | 38827 | 38828 | 38831 | 38832 | 38833 | 38834 | 38835 | 38838 | 38839 | 38840 | 38841 | 38842 | 38845 | 38846 | 38847 | 38848 | 38849 | 38852 | 38853 | 38854 | 38855 | 38856 | 38859 | 38860 | 38861 | 38862 | 38863 | 38866 | 38867 | 38868 | 38869 | 38870 | 38873 | 38874 | 38875 | 38876 | 38877 | 38880 | 38881 | 38882 | 38883 | 38884 | 38887 | 38888 | 38889 | 38890 | 38891 | 38894 | 38895 | 38896 | 38897 | 38898 | 38901 | 38902 | 38903 | 38904 | 38905 | 38908 | 38909 | 38910 | 38911 | 38912 | 38915 | 38916 | 38917 | 38918 | 38919 | 38922 | 38923 | 38924 | 38925 | 38926 | 38929 | 38930 | 38931 | 38932 | 38933 | 38936 | 38937 | 38938 | 38939 | 38940 | 38943 | 38944 | 38945 | 38946 | 38947 | 38950 | 38951 | 38952 | 38953 | 38954 | 38957 | 38958 | 38959 | 38960 | 38961 | 38964 | 38965 | 38966 | 38967 | 38968 | 38971 | 38972 | 38973 | 38974 | 38975 | 38978 | 38979 | 38980 | 38981 | 38982 | 38985 | 38986 | 38987 | 38988 | 38989 | 38992 | 38993 | 38994 | 38995 | 38996 | 38999 | 39000 | 39001 | 39002 | 39003 | 39006 | 39007 | 39008 | 39009 | 39010 | 39013 | 39014 | 39015 | 39016 | 39017 | 39020 | 39021 | 39022 | 39023 | 39024 | 39027 | 39028 | 39029 | 39030 | 39031 | 39034 | 39035 | 39036 | 39037 | 39038 | 39041 | 39042 | 39043 | 39044 | 39045 | 39048 | 39049 | 39050 | 39051 | 39052 | 39055 | 39056 | 39057 | 39058 | 39059 | 39062 | 39063 | 39064 | 39065 | 39066 | 39069 | 39070 | 39071 | 39072 | 39073 | 39076 | 39077 | 39078 | 39079 | 39080 | 39083 | 39084 | 39085 | 39086 | 39087 | 39090 | 39091 | 39092 | 39093 | 39094 | 39097 | 39098 | 39099 | 39100 | 39101 | 39104 | 39105 | 39106 | 39107 | 39108 | 39111 | 39112 | 39113 | 39114 | 39115 | 39118 | 39119 | 39120 | 39121 | 39122 | 39125 | 39126 | 39127 | 39128 | 39129 | 39132 | 39133 | 39134 | 39135 | 39136 | 39139 | 39140 | 39141 | 39142 | 39143 | 39146 | 39147 | 39148 | 39149 | 39150
Initial Preparation |  |  | 2006-04-03 | 2006-04-04 |  | 0% | bar: 2006-04-03 2006-04-03 to 2006-04-03 38811
Receive delegation folder | 1 | 1 | 2006-04-03 | 2006-04-03 |  | 0% | bar: 2006-04-03 2006-04-03
Notify Comptroller of RFP intent and note Representative assigned | 1 | 1 | 2006-04-03 | 2006-04-03 |  | 0% | bar: 2006-04-03 2006-04-03
Notify BSBO of RFP intent and note Representative assigned | 2 | 2 | 2006-04-03 | 2006-04-04 |  | 0% | bar: 2006-04-03 2006-04-03 to 2006-04-03 38811
Notify PIBH (if applicable) | 2 | 2 | 2006-04-03 | 2006-04-04 |  | 0% | bar: 2006-04-03 2006-04-03 to 2006-04-03 38811
Notify Correctional Industries (if applicable) | 2 | 2 | 2006-04-03 | 2006-04-04 |  | 0% | bar: 2006-04-03 2006-04-03 to 2006-04-03 38811
Mobilization |  |  | 2006-04-05 | 2006-04-07 |  | 0% | bar: 2006-04-03 38812 to 2006-04-03 38814
Prepare for meeting with agency |  |  | 2006-04-05 | 2006-04-07 |  | 0% | bar: 2006-04-03 38812 to 2006-04-03 38814
Prepare agenda | 3 | 3 | 2006-04-05 | 2006-04-07 |  | 0% | bar: 2006-04-03 38812 to 2006-04-03 38814
Schedule conference room | 2 | 2 | 2006-04-05 | 2006-04-06 |  | 0% | bar: 2006-04-03 38812 to 2006-04-03 38813
Conduct meeting with agency |  |  | 2006-04-19 | 2006-04-21 |  | 0% | bar: 2006-04-17 38826 to 2006-04-17 38828
Preliminary RFP Questionnaire | 1 | 1 | 2006-04-19 | 2006-04-19 |  | 0% | bar: 2006-04-17 38826
Discuss roles and responsibilities | 1 | 1 | 2006-04-19 | 2006-04-19 |  | 0% | bar: 2006-04-17 38826
Handout confidentiality statements - Collect for file | 1 | 1 | 2006-04-19 | 2006-04-19 |  | 0% | bar: 2006-04-17 38826
Identify Team Members, Stakeholders (Roles & Responsibilities) | 3 | 3 | 2006-04-19 | 2006-04-21 |  | 0% | bar: 2006-04-17 38826 to 2006-04-17 38828
Scope Definition | 3 | 3 | 2006-04-19 | 2006-04-21 |  | 0% | bar: 2006-04-17 38826 to 2006-04-17 38828
Discuss tentative timeline | 3 | 3 | 2006-04-19 | 2006-04-21 |  | 0% | bar: 2006-04-17 38826 to 2006-04-17 38828
Develop timeline |  |  | 2006-04-19 | 2006-04-21 |  | 0% | bar: 2006-04-17 38826 to 2006-04-17 38828
Profile Internally & Externally |  |  | 2006-04-24 | 2006-06-30 |  | 0% | bar: 2006-04-24 38831 to 2006-06-26 38898
Perform Industry Analysis | 11 | 11 | 2006-04-24 | 2006-05-08 | 5 | 0% | bar: 2006-04-24 38831 to 2006-05-08 38845
Create data template to collect spend and pricing | 11 | 11 | 2006-04-24 | 2006-05-08 |  | 0% | bar: 2006-04-24 38831 to 2006-05-08 38845
Send out data template | 1 | 1 | 2006-05-09 | 2006-05-09 |  | 0% | bar: 2006-05-08 38846
Develop and Distribute RFI to suppliers | 18 | 18 | 2006-05-08 | 2006-05-31 | 5 | 0% | bar: 2006-05-08 38845 to 2006-05-29 38868
Develop Profiles for Current and Potential Suppliers | 23 | 23 | 2006-05-31 | 2006-06-30 | 8 | 0% | bar: 2006-05-29 38868 to 2006-06-26 38898
Compile RFI responses and Summarize Supply Market Research | 12 | 12 | 2006-06-15 | 2006-06-30 | 9 | 0% | bar: 2006-06-12 38883 to 2006-06-26 38898
Compile internal data from spend template | 12 | 12 | 2006-06-15 | 2006-06-30 |  | 0% | bar: 2006-06-12 38883 to 2006-06-26 38898
Develop Strategy |  |  | 2006-07-03 | 2006-07-26 |  | 0% | bar: 2006-07-03 38901 to 2006-07-24 38924
Evaluate Current Category/Job Specs and Revise as appropriate | 11 | 11 | 2006-07-03 | 2006-07-17 | 17 | 0% | bar: 2006-07-03 38901 to 2006-07-17 38915
Summarize Sourcing Strategy | 5 | 5 | 2006-07-17 | 2006-07-21 | 19 | 0% | bar: 2006-07-17 38915 to 2006-07-17 38919
Review and Select Sourcing Strategy with Key Stakeholders | 1 | 1 | 2006-07-24 | 2006-07-24 | 22 | 0% | bar: 2006-07-24 38922
Identify and Confirm Scoring Team Members | 3 | 3 | 2006-07-24 | 2006-07-26 | 23 | 0% | bar: 2006-07-24 38922 to 2006-07-24 38924
Screen Suppliers & Selection Factors |  |  | 2006-07-27 | 2006-08-31 |  | 0% | bar: 2006-07-24 38925 to 2006-08-28 38960
Develop Screening Factors | 11 | 11 | 2006-07-27 | 2006-08-10 | 27 | 0% | bar: 2006-07-24 38925 to 2006-08-07 38939
Identify Supplier Qualifications | 11 | 11 | 2006-07-27 | 2006-08-10 | 29 | 0% | bar: 2006-07-24 38925 to 2006-08-07 38939
Develop Supplier Selection Criteria for Tender | 11 | 11 | 2006-07-27 | 2006-08-10 | 31 | 0% | bar: 2006-07-24 38925 to 2006-08-07 38939
Create Tender Decision Matrix Tool (Scorecard) | 11 | 11 | 2006-08-10 | 2006-08-24 | 32 | 0% | bar: 2006-08-07 38939 to 2006-08-21 38953
Confirm Process Adherence to Legal Guidelines/Constraints | 2 | 2 | 2006-08-24 | 2006-08-25 | 33 | 0% | bar: 2006-08-21 38953 to 2006-08-21 38954
Obtain Feedback & Timely Approval of Supplier Selection Criteria | 4 | 4 | 2006-08-28 | 2006-08-31 | 34 | 0% | bar: 2006-08-28 38957 to 2006-08-28 38960
Conduct Tender |  |  | 2006-09-04 | 2007-01-29 |  | 0% | bar: 2006-09-04 38964 to 2007-01-29 39111
Develop RFP Document | 23 | 23 | 2006-09-04 | 2006-10-04 | 34 | 0% | bar: 2006-09-04 38964 to 2006-10-02 38994
Signatures & Approvals for Tender |  |  | 2006-10-04 | 2006-10-20 | 37 | 0% | bar: 2006-10-02 38994 to 2006-10-16 39010
Receive Comptroller sign off | 11 | 11 | 2006-10-04 | 2006-10-18 |  | 0% | bar: 2006-10-02 38994 to 2006-10-16 39008
Receive legal sign off | 11 | 11 | 2006-10-04 | 2006-10-18 |  | 0% | bar: 2006-10-02 38994 to 2006-10-16 39008
Receive agency sign off | 11 | 11 | 2006-10-04 | 2006-10-18 |  | 0% | bar: 2006-10-02 38994 to 2006-10-16 39008
Receive OA/OIT CoP and TAR sign off | 13 | 13 | 2006-10-04 | 2006-10-20 |  | 0% | bar: 2006-10-02 38994 to 2006-10-16 39010
Execute/Advertise/Publish RFP (30 business days) |  |  | 2006-10-23 | 2006-10-23 | 38 | 0% | bar: 2006-10-23 39013
Set up bid due date on BOP bid calendar | 1 | 1 | 2006-10-23 | 2006-10-23 |  | 0% | bar: 2006-10-23 39013
Provide electronic copy to Susan Plecker/Danielle Bonner | 1 | 1 | 2006-10-23 | 2006-10-23 |  | 0% | bar: 2006-10-23 39013
Notify bid room of pending RFP and duties | 1 | 1 | 2006-10-23 | 2006-10-23 |  | 0% | bar: 2006-10-23 39013
Prepare and Conduct Pre-proposal Meeting |  |  | 2006-10-24 | 2006-10-26 | 39 | 0% | bar: 2006-10-23 39014 to 2006-10-23 39016
Confirm conference room | 1 | 1 | 2006-10-24 | 2006-10-24 |  | 0% | bar: 2006-10-23 39014
Prepare agenda | 3 | 3 | 2006-10-24 | 2006-10-26 |  | 0% | bar: 2006-10-23 39014 to 2006-10-23 39016
Confirm attendance of stakeholders, program people, end users | 3 | 3 | 2006-10-24 | 2006-10-26 |  | 0% | bar: 2006-10-23 39014 to 2006-10-23 39016
Receive proposals |  |  | 2006-12-14 | 2007-01-29 |  | 0% | bar: 2006-12-11 39065 to 2007-01-29 39111
Confirm Comptroller/legal attendance | 1 | 1 | 2006-12-14 | 2006-12-14 |  | 0% | bar: 2006-12-11 39065
Open proposals and complete bid tab | 1 | 1 | 2006-12-22 | 2006-12-22 |  | 0% | bar: 2006-12-18 39073
Lock up pricing submittals | 1 | 1 | 2006-12-22 | 2006-12-22 |  | 0% | bar: 2006-12-18 39073
Prepare letter and send SDB submittals to BSBO for scoring | 1 | 1 | 2006-12-22 | 2006-12-23 |  | 0% | bar: 2006-12-18 39073
Distribute technical proposals to committee | 1 | 1 | 2006-12-22 | 2006-12-24 |  | 0% | bar: 2006-12-18 39073
Individual proposal scoring | 16 | 16 | 2006-12-22 | 2007-01-12 |  | 0% | bar: 2006-12-18 39073 to 2007-01-08 39094
Group proposal scoring | 11 | 11 | 2007-01-15 | 2007-01-29 | 40 | 0% | bar: 2007-01-15 39097 to 2007-01-29 39111
Summarize Supplier Responses and Select Supplier(s) for BAFO/Negotiations | 1 | 1 | 2007-01-29 | 2007-01-29 | 41 | 0% | bar: 2007-01-29 39111
Shape and Negotiate Value Propositions |  |  | 2007-01-29 | 2007-02-28 |  | 0% | bar: 2007-01-29 39111 to 2007-02-26 39141
Identify Negotiation Team & Attendees OR Prepare for eAuction | 2 | 2 | 2007-01-29 | 2007-01-30 | 38 | 0% | bar: 2007-01-29 39111 to 2007-01-29 39112
Identify Commonwealth's Least to Most Desirable Outcomes (SWOT Analysis) | 5 | 5 | 2007-01-29 | 2007-02-02 | 42 | 0% | bar: 2007-01-29 39111 to 2007-01-29 39115
Identify Supplier Least to Most Desirable Outcomes; Potential Questions OR Train Suppliers | 5 | 5 | 2007-01-29 | 2007-02-02 | 45 | 0% | bar: 2007-01-29 39111 to 2007-01-29 39115
Prepare Fact Based Negotiation Package | 5 | 5 | 2007-01-29 | 2007-02-02 | 46 | 0% | bar: 2007-01-29 39111 to 2007-01-29 39115
Conduct Negotiations with Suppliers OR Conduct eAuction | 18 | 18 | 2007-02-05 | 2007-02-28 | 47 | 0% | bar: 2007-02-05 39118 to 2007-02-26 39141
Summarize Benefits and Savings Opportunities | 1 | 1 | 2007-02-28 | 2007-02-28 | 49 | 0% | bar: 2007-02-26 39141
Review and Obtain Approval from Key Stakeholders | 1 | 1 | 2007-02-28 | 2007-02-28 | 50 | 0% | bar: 2007-02-26 39141
Implement Agreements |  |  | 2007-03-01 | 2007-05-01 |  | 0% | bar: 2007-02-26 39142 to 2007-03-05 39150
Prepare Contract(s) | 2 | 2 | 2007-03-01 | 2007-03-03 | 38 | 0% | bar: 2007-02-26 39142 to 2007-02-26 39143
Sign and Execute Contracts | 5 | 5 | 2007-03-03 | 2007-04-30 | 51 | 0% | bar: 2007-03-05 39146 to 2007-03-05 39150
Publish New Agreements | 0 | 0 | 2007-05-01 | 2007-05-01 | 54 | 0%
Communicate New Agreements | 0 | 0 | 2007-05-01 | 2007-05-01 |  | 0%

## Key Inputs
Profile Internally & Externally Key Activities | Ownership
Scope Definition
Assessment Analysis of Spend, Key suppliers, Key Agencies |  | DGS
Define Scope of Commodities to be sourced |  | Agency
Identify Users within Key Agencies |  | Coordinated Effort
Internal Data (Invoices, Contracts, Historical Usage)
Cost Reduciton Ideas (CRI) from Users
Survey Key Users/Agencies/Buyers
Industry Analysis Key Activities
Current Suppliers
AP supplier spend data & current contracts
NAICS Classificaitons & data
Industry Publications (Hoovers, IDS, OneSource, etc.)
Conduct industry analysis (Market size, growth, industry trends, etc.)
Identify sub-commodities within commodity
Identify global key industry suppliers and profile each
Identify key internal suppliers & profile each
Conduct a workshop to collect Cost Reduction Ideas from the Agencies (Prioritize & Rank)
Summary of Internal Spend, Requirements, & Specifications Data
Other states contracts
Industry Analysis Key Outputs
Request for Information (RFI)
Supplier Profiles
Industry Analysis (Five Forces Model)
Develop Strategy
Develop Strategy Key Inputs
Cost Reduction Ideas (CRI)
As-Is Process Flows
Summary of Internal Spend, Requirements, & specifications Data
Key Activities
Identify and select critical costs
Categorize critical costs; price, use, administrative
Prepare the total cost of ownership (TCO) model
Gather supporting cost & benchmark data
Analyze data
Establish "target cost" range (low, target, high)
Straw model TCO model & obtain input
FinalizeTCO model
Key Outputs
TCO Model
Key Inputs
Summary of Internal Spend, Requirements & Specifications Data
Industry Analysis (Five Forces Model)
TCO Model
Benchmarking Data
Key Activities
Review key inputs
Select relationship or transactional focus
Identify tactics for concentration of volume
Review Strategy characteristics & tools
Select strategy
Identify tools (E.G. auction, RFP)
Straw model, & obtain input
Key Outputs
Commodity Strategy
Decision of Offer Type
Screen Suppliers & Selection Factors
Screen Suppliers and Selection Factors Key Inputs
Commodity Strategy
Decision of Offer Type
Key agency players
Commodity Business requirements
Typical commodity selection criteria
Key Activities
Select Evaluaiton Team
Identify relevant selection criteria
Conduct "10-4" process
Select Criteria
Rank & weight criteria
Create scorecard
Finalize scorecard
Key Outputs
Weighted scorecard
Technical Requirements
Conduct Offer
Conduct Tender Key Inputs
Total Cost of Ownership (TCO) Components
Commodity Strategy
Weighted Scorecard
Technical Requirements
Key Activities
Determine IFB/RFP scope, timing & contacts
Review historical IFB/RFP
Develop IFB/RFP
Collect & analyze IFB/RFP responses
Q&A period
Key Outputs
Pre-Proposal conference
Populate scorecard
Final Offer Discussions
Pre-proposal conference documents
Fianlized Competitive offer Packages
LDS & MAS Outcomes
Completed Offer Scorecard
Shape & Negotiate Value Propositions
Shape and Negotiate Value Propositions Key Inputs
Competitive Offer (RFP, ITB, etc) Responses
Current Contract
Core Team Feedback
Completed Offer Scorecard
Most Desireable/Least Acceptable options to award
Key Activities
Review "target cost" range
Straw model leverage/discussion points
Identify CWOPA's and the Supplier's least to most desired outcomes & arguments
Prepare BAFO Package
Prepare fact-based negotiation (FBN) Package
Identify negotiation attendees;issue package
Key Outputs
BAFO Package
Fact-Based Negotiation Package
Awared Recommendation
Implement Agreements
Implement Agreements Key Inputs
Final Negotiation/FBN Results
Recommendation of Award
Key Activities
Pre-Contract Signature
Identify Stakeholds & assess impact
Develop Implementation & Communication Plans
Contract Checklist
Post-Contract Signature
Implement Commodity
Measure Supplier Performance
Key Outputs
Implementation Plan
Signed Contract
Contract Checklist & Letter
Supplier Performance Scorecard